## Sprint 1
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
11 | As a user, I want to be able to left click to draw lines so I don’t have to select the toolbar icon. | Implement line drawing | 4 | 4 | F | 2 | N/A - Abandoned | Will 100%
12 | As a user, I want to be able to right click to edit lines so I don’t have to select the toolbar icon. | read rmb from main | 4 | 4 | F | 2 | N/A - Abandoned | Will 100%
15 | As a user, I want a magnifying glass toolbar icon so that I can zoom in and out from the grid. | Implement zoom function | 5 | 5 | F | 8 | 4 | Will 50%
16 | As a user, I want a tool resembling a closed hand so that I can pan my view of the grid. | Implement moving ability | 5 | 5 | F | 8 | 7 | Callen 50%, Will 40%
17 | As a user, I want a tool resembling a house so that I can move back to the part of the grid with my drawings if I get lost in the infinite grid. | Implement point of origin | 5 | 5 | F | 8 | 4 | Will 50%