## Sprint 1
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
6 | As a user, I want an eye dropper toolbar icon so that I can draw new lines with the same values of existing lines to save time. | Add button, add EyeDropper tool | 3 | 3 | F | 4 | 4 | Will 100%
7 | As a user, I want a trash icon so that I can clear my whole grid without having to erase every line. | Add trash icon | 3 | 3 | F | 2 | 2 | Will 100%
8 | As a user, I want an incremented slider to adjust ball speed so that I can make the sounds play faster without modifying the lines to be shorter. | Add orb edit sub-panel to sidebar | 3 | 3 | F | 3 | 0
9 | As a user, I want the application to have a toolbar that allows me to edit the lines’ sound values so that I can adjust pitch, volume, and quality. | Add line edit sub-panel to sidebar | 3 | 3 | F | 3 | 2 | Michael 100%