## Sprint 1
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
8 | As a user, I want an incremented slider to adjust ball speed so that I can make the sounds play faster without modifying the lines to be shorter. | Add orb edit sub-panel to sidebar | 3 | 4 | F | 3 | 3 | Callen 100%
9 | As a user, I want the application to have a toolbar that allows me to edit the lines’ sound values so that I can adjust pitch, volume, and quality. | Add line edit sub-panel to sidebar | 3 | 4 | F | 3 | 3 | Michael 100%
10 | As a user, I want a stamp toolbar icon so that I can duplicate blocks of grid to save time. | Implement duplication | 4 | 4 | F | 5 | 2 | Will 100%
11 | As a user, I want to be able to left click to draw lines so I don’t have to select the toolbar icon. | Implement line drawing | 4 | 4 | F | 2 | 1 | Will 100%
12 | As a user, I want to be able to right click to edit lines so I don’t have to select the toolbar icon. | read rmb from main | 4 | 4 | F | 2 | 1 | Will 100%
13 | As a user, I want incremented sliders to adjust sound values so that I can feel in control and have a visual representation of values. | Add sliders, variables | 4 | 4 | F | 2 | 2 | Will 100%
14 | As a user, I want an orb tool that lets me place new orbs on lines so that I can make more complex music. | Implement orb placement | 4 | 4 | F | 3 | 1 | Will 100%