## Sheet1
| User Story | Sprint Number | Story Priority | Story Status | Story Points | Key
1 | As an internet user, I want to be able to access the application in my browser so I don’t have to download anything | 1 | H | D | 1 | Abandoned
2 | As a user, I want to have a grid so that it is clear where I am able to draw lines. | 2 | H | D | 2 | Done
3 | As a user, I want to have a toolbar with labeled tools on the edge of my screen so I can see my available actions. | 2 | M | D | 3
4 | As a user, I want a pencil toolbar icon so that I can draw lines. | 2 | H | D | 3
5 | As a user, I want an eraser toolbar icon so I can remove lines and orbs quickly. | 2 | H | D | 3
6 | As a user, I want an eye dropper toolbar icon so that I can draw new lines with the same values of existing lines to save time. | 3 | L | D | 4
7 | As a user, I want a trash icon so that I can clear my whole grid without having to erase every line. | 3 | L | D | 2
8 | As a user, I want an incremented slider to adjust orb speed so that I can make the sounds play faster without modifying the lines to be shorter. | 3 | M | D | 3
9 | As a user, I want the application to have a toolbar that allows me to edit the lines’ sound values so that I can adjust pitch, volume, and quality. | 3 | H | D | 3
10 | As a user, I want a stamp toolbar icon so that I can duplicate blocks of grid to save time. | 4 | L | D | 5
11 | As a user, I want to be able to left click to draw lines so I don’t have to select the toolbar icon. | 4 | M | A | 2
12 | As a user, I want to be able to right click to edit lines so I don’t have to select the toolbar icon. | 4 | M | A | 2
13 | As a user, I want incremented sliders to adjust sound values so that I can feel in control and have a visual representation of values. | 4 | M | D | 2
14 | As a user, I want an orb tool that lets me place new orbs on lines so that I can make more complex music. | 4 | L | D | 3
15 | As a user, I want a magnifying glass toolbar icon so that I can zoom in and out from the grid. | 5 | M | A | 8
16 | As a user, I want a tool resembling a closed hand so that I can pan my view of the grid. | 5,6 | M | D | 8
17 | As a user, I want a tool resembling a house so that I can move back to the part of the grid with my drawings if I get lost in the infinite grid. | 5,6 | M | IP | 8
18 | As a beginner user, I want a tutorial to introduce me to the tools so I become familiar with them. | 6 | L | IP | 7
19 | As a user, I want to be able to view and play others’ projects with a URL so I can give them feedback. | 6 | L | IP | 4
21 | As an involved user, I want an infinite workspace so that I can scale my project however large I would like. | 6 | L | D | 9
20 | As a developer, I want to be able to see usage statistics so I can see how many people are using my application. | 7 | L | W | 7
22 | As a developer, I want to be able to receive feedback from the users via email so that I can improve the application. | 7 | L | W | 5