## Sprint 1
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
15 | As a user, I want a magnifying glass toolbar icon so that I can zoom in and out from the grid. | Implement zoom function | 5,6 | N/A Abandonded | F | 8 | 4 | Will 50%
16 | As a user, I want a tool resembling a closed hand so that I can pan my view of the grid. | Implement moving ability | 5,6 | 6 | F | 8 | 7 | Callen 50%, Will 40%
17 | As a user, I want a tool resembling a house so that I can move back to the part of the grid with my drawings if I get lost in the infinite grid. | Implement point of origin | 5,6 | 6 | F | 8 | 4 | Will 50%
18 | As a beginner user, I want a tutorial to introduce me to the tools so I become familiar with them. | Make Tutorial | 6 | 6 | F | 7 | 0 | Not started
19 | As a user, I want to be able to view and play others’ projects with a URL so I can give them feedback. | Export board as a URL | 6 | 6 | F | 4 | 2 | Sam 100%
21 | As an involved user, I want an infinite workspace so that I can scale my project however large I would like. | Make grid infinite | 6 | 6 | F | 9 | 9 | Will 100%